## Project Planner
Planner for Team #5
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (Days starting from Nov.18)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Input Markdown Output Flashcards | 5 | 3 | 10 | 1 | 100%
Share PDF cards to accounts | 13 | 4 | 11 | 1 | 100%
Render Markdown notes | 13 | 3 | 12 | 1 | 100%
Find text in files | 3 | 4 |  |  | 1%
Rename files using regular expressions | 7 | 3 | 9 | 2 | 100%
Track hours worked | 4 | 5 | 6 | 3 | 100%
Visualize hours worked and projects | 12 | 5 | 11 | 1 | 93%
Convert Markdown to PDF | 9 | 2 | 12 | 1 | 88%
Share notes with other users | 13 | 3 |  |  | 15%
Create time blocks | 16 | 5 |  |  | 0%
Pomodoro timer | 1 | 3 | 2 | 3 | 100%
Mind map of flash cards | 8 | 5 | 7 | 5 | 10%
Change order of flash cards by correctness | 13 | 4 |  |  | 0%
Create pdf of flash cards to print | 10 | 2 | 11 | 3 | 100%
Add todo tracker | 9 | 2 | 9 | 1 | 100%